## Work Pack 4
WORK PACK FOUR - Melton Plant Hire
Damage Number | Damage Type | Location Type 2 | Location Type 1 | Primary Location | Location | Chainage From | Chainage To | Damage Details | Priority | Quantity | Second Quantity | Second Unit of Measure | Latitude | Longitude | Estimated $ | % Complete | Restoration report completed (Y/N) | Actual Completion | Invoice Amount | Precondtion Report | Precondition approved MSC | Estimate | Submitted VR | Approved (VR) | Est Start | Est Completion
DM00056 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Egerton Road | RDS_003819 | 4.55 | 4.55 |  | M | 200 | 100 | depth mm | -37.6298 | 144.1611 | 5888.5 |  |  |  |  | 2019-05-14 | TM | 2019-05-14
DM00103 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 4.07 | 4.07 |  | M | 8 | 375 | diameter | -37.6598 | 144.2013 | 4224.07
DM00109 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_005005 | 1.69 | 1.69 |  | M | 10 | 300 | diameter | -37.6386 | 144.2047 | inc
DM00096 | SEALED PAVEMENT DAMAGE | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003776 | 2.23 | 2.23 | Excess loose material on the seal | M | 50 | 0 |  | -37.6434 | 144.2033 | inc
DM00101 | SEALED PAVEMENT DAMAGE | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 3.45 | 3.45 |  | M | 50 | 0 |  | -37.6542 | 144.2015 | inc
DM00110 | TABLE DRAIN DAMAGED OR DESTROYED | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_005005 | 1.89 | 1.89 |  | M | 100 | 0 |  | -37.6404 | 144.2042 | 3781
DM00100 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 3.46 | 3.46 |  | M | 10 | 200 | depth mm | -37.6543 | 144.2015 | inc
DM00108 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_005005 | 1.18 | 1.18 |  | M | 50 | 50 | depth mm | -37.6342 | 144.2064 | 31164.1429
DM00094 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003776 | 2.15 | 2.15 |  | M | 50 | 50 | depth mm | -37.6427 | 144.2035 | inc
DM00102 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 3.9 | 3.9 |  | M | 75 | 50 | depth mm | -37.6582 | 144.2013 | inc
DM00097 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 2.59 | 2.59 |  | M | 100 | 200 | depth mm | -37.6465 | 144.2023 | inc
DM00099 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Ballan-Meredith Road | RDS_003777 | 2.92 | 2.92 | Shoulders on both sides | M | 200 | 50 | depth mm | -37.6494 | 144.2018 | inc
DM00583 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Ballan | Bences Lane | RDS_005788 | 2.35 | 2.35 | Outlet blocked with silt | M | 11 | 450 | diameter | -37.5895 | 144.2594 | 2658.455
DM00111 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Ballan | Hasties Lane | RDS_006056 | 0.32 | 0.32 |  | M | 9 | 300 | diameter | -37.6198 | 144.2077 | 1606.89
DM00142 | UNSEALED ROAD SURFACE DAMAGED - LOSS OF MATERIALS | Central Moorabool | Ballan | Hasties Lane | RDS_006056 | 0.22 | 0.22 |  | M | 70 | 150 | depth mm | -37.6199 | 144.2089 | 17105.1
DM00143 | UNSEALED ROAD SURFACE DAMAGED - LOSS OF MATERIALS | Central Moorabool | Ballan | Hasties Lane | RDS_006056 | 0.31 | 0.31 |  | M | 120 | 150 | depth mm | -37.6198 | 144.2079 | inc
DM00141 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Hasties Lane | RDS_006056 | 0.02 | 0.02 |  | M | 10 | 100 | depth mm | -37.6201 | 144.2111 | inc
DM00268 | UNSEALED SHOULDER SURFACE DAMAGE - LOSS OF MATERIALS | Central Moorabool | Ballan | Old Geelong Road | RDS_004066 | 0.63 | 0.63 |  | M | 8 | 150 | depth mm | -37.6059 | 144.2171 | 2689.4643
DM00559 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Balliang | Reids Road | RDS_005580 | 12.19 | 12.19 |  | M | 10 | 225 | diameter | -37.7608 | 144.2688 | 10631.75
DM00562 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Rowsley | Reids Road | RDS_004540 | 0.14 | 0.14 | Blockev with silt | M | 10 | 225 | diameter | -37.7357 | 144.3804 | inc
DM00560 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Rowsley | Reids Road | RDS_003972 | 5.82 | 5.82 | Culvert fully blocked | M | 10 | 225 | diameter | -37.738 | 144.3235 | inc
DM00561 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Rowsley | Reids Road | RDS_004540 | 0.38 | 0.38 | Inlet and outlet blocked with silt | M | 10 | 225 | diameter | -37.7354 | 144.3777 | inc
DM00563 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Rowsley | Reids Road | RDS_004540 | 0.01 | 0.01 | Outlet blocked with silt | M | 10 | 300 | diameter | -37.7355 | 144.3818 | inc
DM00537 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.3 | 1.3 | Inlet blocked | M | 7 | 300 | diameter | -37.8125 | 144.2828 | 5033.91
DM00538 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.13 | 1.13 | Inlet blocked | M | 7 | 300 | diameter | -37.8131 | 144.2844 | inc
DM00534 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.6 | 1.6 | Inlet blocked | M | 8 | 450 | diameter | -37.811 | 144.281 | inc
DM00533 | TABLE DRAIN DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.89 | 1.89 | Table drain blocked from erroion | M | 5 | 0 |  | -37.8114 | 144.2799 | 4536.25
DM00536 | TABLE DRAIN DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.35 | 1.35 | Table drain blocked, may cause further damage to road surface in next flood event | M | 10 | 0 |  | -37.8122 | 144.2823 | inc
DM00539 | TABLE DRAIN DAMAGED OR DESTROYED | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 0.87 | 0.87 | Table drain washed away and formed depth upto 700mm at the edge of the road | M | 50 | 0 |  | -37.8138 | 144.287 | inc
DM00535 | UNSEALED ROAD SURFACE DAMAGED - LOSS OF MATERIALS | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 1.58 | 1.58 |  | M | 70 | 125 | depth mm | -37.8109 | 144.2812 | 23054.92
DM00540 | UNSEALED ROAD SURFACE DAMAGED - LOSS OF MATERIALS | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 0.8 | 0.8 | Scouring and pothole formed on unsealed surface | M | 150 | 100 | depth mm | -37.8138 | 144.2878 | inc
DM00532 | UNSEALED ROAD SURFACE DAMAGED - LOSS OF MATERIALS | Central Moorabool | Balliang | Thompsons Road | RDS_005745 | 2.16 | 2.16 | Significant loss of material from the surface, loose big stones, may need resheeting or compaction | M | 200 | 100 | depth mm | -37.8091 | 144.2806 | inc
DM00552 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Beremboke Road | RDS_005571 | 6.44 | 6.44 |  | M | 7 | 300 | diameter | -37.8029 | 144.2308 | 8218.435
DM00553 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Beremboke Road | RDS_005571 | 5.98 | 5.98 | Inlet fully under silt | M | 10 | 225 | diameter | -37.802 | 144.2345 | inc
DM00554 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Beremboke Road | RDS_005571 | 5.36 | 5.36 | Inlet blocked | M | 10 | 300 | diameter | -37.7976 | 144.238 | inc
DM00555 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Camerons Lane | RDS_005576 | 0.92 | 0.92 | Inlet blocked | M | 11 | 300 | diameter | -37.798 | 144.2536 | 8379.935
DM00558 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Camerons Lane | RDS_003964 | 2.83 | 2.83 | Inlet blocked | M | 15 | 300 | diameter | -37.8092 | 144.2622 | inc
DM00557 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Camerons Lane | RDS_003964 | 1.46 | 1.46 | Inlet blocked | M | 20 | 300 | diameter | -37.8003 | 144.2575 | inc
DM00556 | LOSS OF MATERIAL AT SITE REQUIRING REPLACEMENT | Central Moorabool | Beremboke | Combridge Drive | RDS_003965 | 1.03 | 1.03 | 1m Deep ditch formed on the side of the shoulder | M | 1 | 0 |  | -37.8067 | 144.2525 | 2918.835
DM00570 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Leveretts Lane | RDS_005778 | 0.01 | 0.01 | Inlet blocked | M | 6 | 225 | diameter | -37.7968 | 144.2118 | 2755.36
DM00571 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Marshalls Lane | RDS_005816 | 0.92 | 0.92 | Inlet blocked | M | 5 | 225 | diameter | -37.8113 | 144.2328 | 6316.005
DM00572 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Marshalls Lane | RDS_005573 | 1.83 | 1.83 | Inlet fully under silt | M | 5 | 225 | diameter | -37.8112 | 144.2381 | inc
DM00551 | PIPE CULVERT DAMAGED OR DESTROYED | Central Moorabool | Beremboke | Marshalls Lane | RDS_005573 | 1.44 | 1.44 | Outlet half blocked | M | 5 | 225 | diameter | -37.8091 | 144.2363 | inc
[11 empty] | Total Ex. GST |  |  |  | 140963.0221 | 0